## Slide 1
MERIDIAN
TECHNOLOGY GROUP
PROPOSAL · APRIL 2026
Bursary Assessment Platform
A purpose-built replacement for Symplectic Grant Tracker
Prepared for
John Whitgift Foundation
29 April 2026

## Slide 2
MERIDIAN
TECHNOLOGY GROUP
STATUS
Where we are today
Meridian Technology Group · John Whitgift Foundation
02 / 10
The system is substantially built. Today is about hardening, contracts, and migration.
01
Foundations
COMPLETE
Schema, auth, layout shells
02
Core Platform
COMPLETE
Portal, assessment engine, recommendations
03
Operational
COMPLETE
Exports, reports, audit, GDPR, PDF
04
Production
IN FLIGHT
Hardening, UAT, go-live
36
routes built
100%
Must-Have features
0
TypeScript errors
≥10
calc test cases

## Slide 3
MERIDIAN
TECHNOLOGY GROUP
TIMELINE
Path to production · end of June 2026
Meridian Technology Group · John Whitgift Foundation
03 / 10
Nine-week runway · four gates
G1
11 May
Initial Release
Beta on staging
G2
18 May → 12 Jun
User Acceptance
Assessor validation
≥10 calc cases
G3
15 → 22 Jun
Pre-Prod Hardening
GDPR · perf · security
G4
End June
Production Go-Live
Cutover · 2-wk hypercare
Migration from Grant Tracker runs as a parallel workstream — see slide 9.

## Slide 4
MERIDIAN
TECHNOLOGY GROUP
COMMERCIAL
Headline terms
Meridian Technology Group · John Whitgift Foundation
04 / 10
INITIAL BUILD
£5,000
One-off · 100% on contract signature
ANNUAL LICENSE
£7,000
Year 1 invoiced on go-live · annually thereafter
MIGRATION
Custom
Discovery-led · separately scoped
PAYMENT CADENCE
Build on contract signature · Year 1 licence on go-live (end June 2026) · Net 30 day terms

## Slide 5
MERIDIAN
TECHNOLOGY GROUP
LICENCE FEE
Transparent build-up
Meridian Technology Group · John Whitgift Foundation
05 / 10
Built bottom-up from real costs · no hidden margin on infrastructure
INFRASTRUCTURE
~ £1,000 / year
Vercel Pro
Production hosting · edge · zero-downtime
£200
Supabase Pro
Postgres · auth · storage · daily backup
£240
Resend
Transactional email
£190
Sentry
Error monitoring
£250
Domain & SSL
Custom domain
£20
Headroom
Traffic & overage buffer
£100
MAINTENANCE
£6,000 / year
£500 / month allocation
Bug fixes
Security patches & dependency updates
Reference table tweaks
Minor enhancements
Ad-hoc support requests
Quarterly review meetings
TOTAL ANNUAL LICENCE
£7,000 / year

## Slide 6
MERIDIAN
TECHNOLOGY GROUP
SCOPE
What maintenance covers
Meridian Technology Group · John Whitgift Foundation
06 / 10
INCLUDED
No additional charge
Bug fixes & regressions
Security patches
Dependency updates
Reference table tweaks
Minor enhancements
Ad-hoc support questions
Annual GDPR review support
QUOTED SEPARATELY
Custom scope
New major features
Phase 2 roadmap items
Calculation model changes
Integrations with external systems
Data migrations beyond Grant Tracker
Bespoke reporting builds

## Slide 7
MERIDIAN
TECHNOLOGY GROUP
SUPPORT
Reliable communication, real coverage
Meridian Technology Group · John Whitgift Foundation
07 / 10
TICKETING
Freshdesk
Email-to-ticket · self-service portal · full SLA audit trail
COVERAGE
Team-backed
Brian as primary contact · outsourced engineering team scaled on demand
RESPONSE SLA
Severity-based, working hours Mon–Fri 09:00–17:30 UK
SEVERITY
EXAMPLE
RESPOND
RESOLVE
CRITICAL
System down during a round
4 working hours
1 working day
HIGH
Major feature broken
1 working day
3 working days
MEDIUM
Minor bug · workaround exists
2 working days
Next maintenance cycle
LOW
Question · suggestion
5 working days
Quarterly review

## Slide 8
MERIDIAN
TECHNOLOGY GROUP
SECURITY
Built in, not bolted on
Meridian Technology Group · John Whitgift Foundation
08 / 10
GDPR-aligned by design · the data is sensitive · the controls are real
Encryption
TLS in transit · AES-256 at rest
MFA
Mandatory for all admin accounts
RBAC
Applicants see only their own data
Data Minimisation
Names hidden by default · reveals audit-logged
Document Access
Pre-signed time-limited URLs
Audit Trail
Immutable log of every CRUD operation
UK / EU Hosting
GDPR-compliant data residency
Retention
7-year retention · right-to-deletion
Backups
Daily automated · 30-day PITR
OWASP
Top-10 hardening · CSP · rate limiting
Virus Scanning
All uploads scanned before storage
Independent Review
GDPR sign-off at G3 before go-live

## Slide 9
MERIDIAN
TECHNOLOGY GROUP
MIGRATION
From Grant Tracker · custom workstream
Meridian Technology Group · John Whitgift Foundation
09 / 10
Grant Tracker is sunset 31 Dec 2026 · we have runway, but discovery comes first
01
Discovery Sprint
1–2 weeks · fixed price
Audit Grant Tracker exports.
Document data shape.
Identify migration risks.
02
Fixed Quote
Based on findings
Extract → transform → load.
Scope confirmed.
Timeline aligned with go-live.
03
Cutover
100% migrated
Active accounts moved.
20% spot-checked.
Reference numbers preserved (WS-/TS-).
WHAT MOVES ACROSS
Active bursary accounts
Historical assessments
Documents
Sibling linkages
Benchmark fees

## Slide 10
MERIDIAN
TECHNOLOGY GROUP
NEXT STEPS
Where we go from here
1
Confirm acceptance of commercial terms
2
Schedule UAT kick-off — w/c 18 May 2026
3
Initiate Grant Tracker migration discovery
4
Confirm Freshdesk onboarding
5
Sign go-live date — end of June 2026
Brian Wagner · Meridian Technology Group
meridiantech.group